## CONTACTS
"YOUR EVENT" Contacts
Section | Who | Name | What for | Phone | Email
"YOUR EVENT" EXEC |  | EVENT COORDINATOR | EVENT COORDINATOR
"YOUR EVENT" EXEC |  | Finance Coordinator | Finance Coordinator
"YOUR EVENT" EXEC |  | FOF Treasurer | FOF Treasurer
"YOUR EVENT" EXEC |  | Marketing | Marketing
"YOUR EVENT" EXEC |  | Secretary / MC | Secretary / MC
BAR | Liquor Licence |  | Licencing
BAR | Bar suppliers |  | Supply beer at cost
BBQ |  |  | Owner-bakery
BBQ |  |  | Owners-butcher
CHILDREN |  |  | Sponsorship
CHILDREN | Face Painter | Sparkles
ENTERTAINER |  |  | Celebrity Chef
ENTERTAINER |  |  | Celebrity Chef
ENTERTAINER |  |  | Celebrity Gardener
ENTERTAINER |  |  | Celebrity Gardener
ENTERTAINER |  |  | Entrance display/grows herbs for cooking demo
ENTERTAINER |  |  | Supply cooking equipment – inkind support
MARKETING |  |  | advertising
MARKETING |  |  | advertising
MARKETING |  |  | Covers printing costs -to agreed amount
MARKETING |  |  | Event liaison
MARKETING |  |  | Inkind support (printing of volunteer tags)
MARKETING |  |  | Jam labels/car/bus stickers
MARKETING |  |  | Marketing
MARKETING |  |  | Sponsor –graphic design
MARKETING |  |  | Sponsor-bus shuttles/stickers on bus
MARKETING |  |  | Sponsor/BBQ/tents
MARKETING |  |  | Sponsorship
MARKETING |  |  | Web sponsor
MC |  |  | Audio visual
MC |  |  | Sound
MUSIC | Music Coordinator |  | Coordinator
MUSIC | APRA |  | Licencing
OPERATIONS | ATM |  | $$$
OPERATIONS |  |  | Audio visual
OPERATIONS | Water Truck |  | Dusty Road
OPERATIONS |  |  | Entrance display/grows herbs for cooking demo
OPERATIONS | Environmental Health Officer |  | Event Planning
OPERATIONS | St John’s |  | First Aid
OPERATIONS |  |  | Local farmer and he brings a beef cow and calf for display at the "YOUR EVENT" and is on the show society committee
OPERATIONS | Portable Toilets |  | Portaloos
OPERATIONS |  |  | Property Owner
OPERATIONS | Car Parking |  | Property Owner
OPERATIONS | Event hire |  | MARQUEES
OPERATIONS | Sand supplier for kids sandpit |  | Sand
OPERATIONS | Toowoomba Regional Council |  | Senior Admin Officer
OPERATIONS | Master Hire |  | Site equipment
OPERATIONS |  |  | Sound
OPERATIONS |  |  | Tents/tills etc
OPERATIONS |  |  | Traffic
OPERATIONS | Road corridor Permit |  | Traffic
PRESERVES |  |  | Jam labels/car/bus stickers
PRODUCE |  |  | Produce Supply
RAFFLES |  |  | Donate raffle
RAFFLES |  |  | Raffle Prize
VOLUNTEERS |  |  | Inkind support (printing of volunteer tags)

## 4 weeks to go
AREA RESPONSIBLE | KEY TASK & MILESTONES - Those in RED require a RUN SHEET | TIMELINE | ✔ | IS A RUN SHEET REQUIRED?
Bar | Arrange ice and trough for the bar Ordered through Clifton Ice and delivered on the day Ice ordered · 12 16kg bags · 12 4kg bags (3 extras free so total of 15 bags) Trough – Felton Hall (may need a bigger one) | 1 month before festival
Bar | Determine pricing and prepare signage | 1 month before festival
Bar | Contact your volunteers prior to the event and ensure they are aware of any RSA matters and are prepared for their shift (volunteer coordinator to provide contacts). This will ensure that problems with inability to make it are addressed before festival - try and prevent volunteers pulling out the morning of. Ensure they are invited to the volunteer thank you function at the end of the festival. | 1 month before festival
BBQ | Contact all your allocated volunteers prior to the event and ensure they are aware of requirements, timing and are prepared for their shift (volunteer coordinator to provide contacts). Ensure they are invited to the volunteer thank you function at the end of the festival. | 1 month before festival
BBQ | Liaise with the volunteer coordinator to allocate volunteers to the BBQ roles. | 1 month before festival
BBQ | Liaise with Operations Coordinator to determine if SES meals are required and what time- schedule into run sheet for festival day. | 1 month before festival
BBQ | Order all food requirements | 1 month before festival
BBQ | Order/purchase paper bags for bacon/egg burgers | 1 month before festival
BBQ | Plan the movement of people in order to effectively manage queues | 1 month before festival
BBQ | Ensure you have all equipment for the event – price stickers, pens, scissors, bags, etc · x2 tills · x5 tables (x3 for display, x2 for storage and pricing); x2 "YOUR EVENT" tablecloths · x2 boxes pricing labels (Office Works $6.99ea), marking pens, biros, scissors, knife · Paper/plastic bags for customers who haven’t come prepared | 1 month before festival
CHILDREN | Contact all your allocated volunteers prior to the event and ensure they are aware of requirements, timing and are prepared for their shift (volunteer coordinator to provide contacts). Ensure they are invited to the volunteer thank you function at the end of the festival. | 1 month before festival
CHILDREN | Kids competitions - send reminders to schools and promote via social media etc | 1 month before festival
"YOUR EVENT" EXEC | Contact all Information and Troubleshooter volunteers prior to the event and ensure they are aware of requirements, timing and are prepared for their shift (volunteer coordinator to provide contacts). Ensure they are invited to the volunteer thank you function at the end of the festival. | 1 month before festival
"YOUR EVENT" EXEC | "YOUR EVENT" Co-ordinators meeting | 1 month before festival |  | Yes - Refer Coordinator Meeting Minutes
"YOUR EVENT" EXEC | "YOUR EVENT" pre event meeting | 1 month before festival |  | Yes - Refer Relevant Meeting Minutes
"YOUR EVENT" EXEC | Finalise Logistics inc. run sheets, rosters, MC notes, checklists, etc | 1 month before festival
"YOUR EVENT" EXEC | Programs and site maps ready for hand out on the day + large copies for display at entrances and info tent | 1 month before festival
"YOUR EVENT" EXEC | "YOUR EVENT" committee and stakeholder debrief meetings - Co-ordinators briefing – a formal briefing meeting so that all co-ordinators understand the complexity of the other co-ordinators roles – the aim is to ensure everyone is working together. | 1 month before festival |  | Yes - Refer Relevant Meeting Minutes
"YOUR EVENT" EXEC | Briefing with Volunteers, Committee, Stakeholder. Be sure to invite them to post festival thank you function | 1 month before festival |  | Yes - Refer Relevant Meeting Minutes
"YOUR EVENT" EXEC | Organise Opening Ceremony | 1 month before festival |  | Yes - Refer Opening Night Run Sheet
"YOUR EVENT" EXEC | Info tent planned and everything ready to set it up | 1 month before festival
"YOUR EVENT" EXEC | Review risk management plan and ensure all coordinators are thoroughly briefed | 1 month before festival
"YOUR EVENT" EXEC | Order all water for the festival for all "YOUR EVENT" Stalls | 1 month before festival
"YOUR EVENT" EXEC | MC + Operations Co-ordinator to meet sound and vision people to finalise requirements | 1 month before festival
"YOUR EVENT" EXEC | Surveys developed and online - visitors, stallholders, sponsors | 1 month before festival
FINANCE | Contact all your allocated volunteers prior to the event and ensure they are aware of requirements, timing and are prepared for their shift (volunteer coordinator to provide contacts). Ensure they are invited to the volunteer thank you function at the end of the festival. | 1 month before festival
FINANCE | One week prior to the festival - Withdraw floats and set them up | 1 month before festival
FINANCE | Work with Stallholder Coordinator to invoice & receive stallholder payments –send receipts to stall holder coordinator and follow up on late payments | Ongoing
MAIN MARQUEE | Contact all your allocated volunteers prior to the event and ensure they are aware of requirements, timing and are prepared for their shift (volunteer coordinator to provide contacts). Ensure they are invited to the volunteer thank you function at the end of the festival. | 1 month before festival
MAIN MARQUEE | - Organise run sheet and MC notes including list of producers and supporters | 1 month before festival
MAIN MARQUEE | - Obtain/collect pantry items. | 1 month before festival
MARKETING | Pre festival short lead PR | 1 month before festival
MARKETING | Newsletter - Checklist on what you need to prepare and what to bring | 1 month before festival
MARKETING | Advertising to commence this month - TV and Radio (start FH March) | 1 month before festival
MARKETING | Pre Event Newsletter - weather, maps/getting to the event, Instagram/hashtag, see you soon! | 1 month before festival
MC | Liaise with the "YOUR EVENT" Exec to finalise the announcer run sheets and notes including sponsor announcements | 1 month before festival |  | Yes - liaise with MC and align with Program and Marketing team
MC | Liaise with Stallholder Coordinator to prepare a list of "YOUR EVENT" stalls that need promotion | 1 month before festival
MC | Work with Marketing Coordinator to prepare a list of sponsors needing acknowledgment | 1 month before festival
MERCHANDISE | Contact all your allocated volunteers prior to the event and ensure they are aware of requirements, timing and are prepared for their shift (volunteer coordinator to provide contacts). Ensure they are invited to the volunteer thank you function at the end of the festival. | 1 month before festival
MERCHANDISE | Some merchandise to be located at other strategic places around festival site - e.g. bar for stubby holders, insulated bags with stalls selling product to keep cold - to be pre arranged with relevant coordinators | 1 month before festival
OPERATIONS | Contact all your Parking, Site Prep volunteers prior to the event and ensure they are aware of requirements, timing and are prepared for their shift (volunteer coordinator to provide contacts). Ensure they are invited to the volunteer thank you function at the end of the festival. | 1 month before festival
OPERATIONS | Contact water truck for managing dust. Russell will supply a driver – probably himself. | 1 month before festival
OPERATIONS | Arrange fencing plan between and within car park and entrance to ensure visitors enter through 1 of 2 entrances (at the northern and southern entrances to the site). | 1 month before festival
OPERATIONS | Arrange fencing plan around back of Main Marquee to stop people entering here | 1 month before festival
OPERATIONS | Order enough walkie talkies for all "YOUR EVENT" Coordinators and "YOUR EVENT" Troublshooters (liaise with Stallholder Coordinator for troubleshooter numbers) | 1 month before festival
OPERATIONS | Communicate with Property Owners regularly about the festival & site preparation activities - follow up regular mowing leading up to the Festival | Ongoing
OPERATIONS | Prepare car parking area/s - clear of rocks, sticks, holes, etc. | Ongoing
OPERATIONS | Regular communication with infrastructure providers to develop a good working relationship and keep abreast of new requirements as required | Ongoing
OPERATIONS | Develop and maintain an inventory of Stall needs and Infrastructure providers eg suppliers of tents/tables/chairs/cash drawers etc | Ongoing
PRODUCE | Contact all your allocated volunteers prior to the event and ensure they are aware of requirements, timing and are prepared for their shift (volunteer coordinator to provide contacts). Ensure they are invited to the volunteer thank you function at the end of the festival. | 1 month before festival
PRODUCE | Arrange delivery of fresh produce to site for pick up on Saturday, store in a coolroom overnight | 1 month before festival
PRODUCE | Maintain a database of producers contacts and the produce supplied | Ongoing
RAFFLES | Contact all your allocated volunteers prior to the event and ensure they are aware of requirements, timing and are prepared for their shift (volunteer coordinator to provide contacts). Ensure they are invited to the volunteer thank you function at the end of the festival. | 1 month before festival
RAFFLES | Contact all stallholders providing prizes for collection either prior to festival or on the day and ensure they are aware of requirements, timing and are prepared for collection | 1 month before festival
SIGNAGE | Contact all your allocated volunteers prior to the event and ensure they are aware of requirements, timing and are prepared for their shift (volunteer coordinator to provide contacts). Ensure they are invited to the volunteer thank you function at the end of the festival. | 1 month before festival
SIGNAGE | Buy necessary supplies and equipment for site signage erection | 1 month before festival
SIGNAGE | Erect all direction signage as per the Signage Plan - with help of volunteers | 1 month before festival
STALLHOLDERS | Contact all your allocated volunteers prior to the event and ensure they are aware of requirements, timing and are prepared for their shift (volunteer coordinator to provide contacts). Ensure they are invited to the volunteer thank you function at the end of the festival. | 1 month before festival
STALLHOLDERS | Finalise any last minute details with Site Plan | 1 month before festival
STALLHOLDERS | Ensure all Stallholders are completely up to date with all paperwork, insurance and food licences - finalise database - all paperwork to be complete - all payments received now. | 1 month before festival
STALLHOLDERS | Ensure Operations Coordinator has ordered enough Walkie Talkies for all direct stallholder volunteers | 1 month before festival
STALLHOLDERS | Attend festivals throughout year looking for new/potential stallholders. Network with existing stall holders | Ongoing
STALLHOLDERS | Check the list of goods intended to be sold by the stall holder listed on their application form– refuse some product if they don’t fit in with values of "YOUR EVENT" eg craft, product not made by stall holder or multi components eg coffee, biscuits, preserves etc. | Ongoing
STALLHOLDERS | Update database when applications are sent in. note power requirements and size of area needed | Ongoing
STALLHOLDERS | Respond to stall holder applications, questions, deny stalls if they don’t fit with "YOUR EVENT" values. | Ongoing
VOLUNTEERS | Ensure all volunteer rosters finalised with enough volunteers schedule for set up and post event clean up | 1 month before festival
VOLUNTEERS | Email a Thankyou to all volunteers for their support and attach an invite for volunteer wrap up (see ‘final letter to coordinator’ and ‘final letter to volunteers’) | 1 month before festival
VOLUNTEERS | Maintain the volunteer roster; liaise with Coordinators to look at the gaps and consider how to fill them. Regularly recruit new volunteers. | Ongoing
VOLUNTEERS | Coordinate Volunteer Thankyou Party post event | 1 month before festival |  | Run Sheet Required

## 2 weeks to go
AREA RESPONSIBLE | KEY TASK & MILESTONES | TIMELINE | ✔ | IS A RUN SHEET REQUIRED?
Bar | Send float break down request to FINANCE 2 weeks prior to the festival | Festival - 2 weeks before
BBQ | Send float break down request to FINANCE 2 weeks prior to the festival | Festival - 2 weeks before
"YOUR EVENT" EXEC | Finalise Survey's and get ready to post online | Festival - 2 weeks before
"YOUR EVENT" EXEC | Organise Opening Ceremony | Festival - 2 weeks before |  | Yes - Refer Opening Night Run Sheet
FINANCE | Send email to all Coordinators reminding them for float breakdown - pricing from all Stall Coordinators is required. Receive all float breakdown requests- chase up if required to ensure all ready to put floats together - keep in mind that pricing has a large effect on what is required in the float | Festival - 2 weeks before
FINANCE | Work with Stallholder Coordinator to invoice & receive stallholder payments –send receipts to stall holder coordinator and follow up on late payments | Ongoing
MAIN MARQUEE | Make lists of produce providers for celebrities to endorse and email it to them | Festival - 2 weeks before
MAIN MARQUEE | - Make signs/labels for produce donations | Festival - 2 weeks before
MAIN MARQUEE | - Organise furniture | Festival - 2 weeks before
MAIN MARQUEE | - Organise/create program signage | Festival - 2 weeks before
MAIN MARQUEE | - Organize equipment for clean up | Festival - 2 weeks before
MAIN MARQUEE | Remind Chefs with requirements of “employment” and expectations | Festival - 2 weeks before
MERCHANDISE | Send float break down request to FINANCE 2 weeks prior to the festival | Festival - 2 weeks before
OPERATIONS | Signs not to be erected until 1-2 weeks before festival and must be removed within 1 week post festival | Festival - 2 weeks before
OPERATIONS | Communicate with PROPERTY OWNERS regularly about the festival & site preparation activities - follow up regular mowing leading up to the Festival | Ongoing
OPERATIONS | Prepare car parking area/s - clear of rocks, sticks, holes, etc. | Ongoing
OPERATIONS | Regular communication with infrastructure providers to develop a good working relationship and keep abreast of new requirements as required | Ongoing
OPERATIONS | Develop and maintain an inventory of Stall needs and Infrastructure providers eg suppliers of tents/tables/chairs/cash drawers etc | Ongoing
PRODUCE | Arrange signage for pricing + visit fruit shop the week prior to determine market value prices (we make sure we are les than this) | Festival - 2 weeks before
PRODUCE | Send float break down request to FINANCE 2 weeks prior to the festival | Festival - 2 weeks before
PRODUCE | Touch base with producers two weeks prior to the festival and see what they will have for collection next Saturday | Festival - 2 weeks before
PRODUCE | Maintain a database of producers contacts and the produce supplied | Ongoing
RAFFLES | Arrange delivery of prizes | Festival - 2 weeks before
RAFFLES | Send float break down request to FINANCE 2 weeks prior to the festival | Festival - 2 weeks before
STALLHOLDERS | Invite some select stallholders to set up on Saturday where possible. By invitation only to alleviate the rush on Sunday | Festival - 2 weeks before
STALLHOLDERS | Attend festivals throughout year looking for new/potential stallholders. Network with existing stall holders | Ongoing
STALLHOLDERS | Check the list of goods intended to be sold by the stall holder listed on their application form– refuse some product if they don’t fit in with values of "YOUR EVENT" eg craft, product not made by stall holder or multi components eg coffee, biscuits, preserves etc. | Ongoing
STALLHOLDERS | Update database when applications are sent in. note power requirements and size of area needed | Ongoing
STALLHOLDERS | Respond to stall holder applications, questions, deny stalls if they don’t fit with "YOUR EVENT" values. | Ongoing
TEA & COFFEE | Send float break down request to FINANCE 2 weeks prior to the festival | Festival - 2 weeks before
VOLUNTEERS | Complete final rosters and send to each volunteer with induction pack (sign on/off, food handling guidelines, exact area they are working, etc). Also provide their coordinators contacts and encourage them to make contact direct with any questions. | Festival - 2 weeks before
VOLUNTEERS | Maintain the volunteer roster; liaise with Coordinators to look at the gaps and consider how to fill them. Regularly recruit new volunteers. | Ongoing
Run Sheet Required

## 1 week to go
AREA RESPONSIBLE | KEY TASK & MILESTONES | TIMELINE | ✔ | IS A RUN SHEET REQUIRED?
BBQ | Ensure Food Handling signage is ready for display on festival day. Purchase adequate soap and hand towels for hand washing | Festival - 1 week before
FINANCE | Work with Stallholder Coordinator to invoice & receive stallholder payments –send receipts to stall holder coordinator and follow up on late payments | Ongoing
"YOUR EVENT" EXEC | Organise Opening Ceremony | Festival - 1 week before |  | Yes - Refer Opening Night Run Sheet
MAIN MARQUEE | Obtain/collect ingredients from stallholders, local farmers, reputable Australian sources via a supermarket/supplier. | Festival - 1 week before
MAIN MARQUEE | - Organise Wash up area (including hand wash facilities) | Festival - 1 week before
MAIN MARQUEE | Equipment - Make sure equipment is all present and clean ready for use - Store equipment easy to be sourced by chefs and volunteers | Festival - 1 week before
MAIN MARQUEE | - Put up marquee and seating | Festival - 1 week before
MC | Develop MC notes | Festival - 1 week before |  | Yes - liaise with MC and align with Program and Marketing team
MUSIC | Make contact with performers one week prior to the festival, updating them on the schedule, reminding them to bring water, and recapping about power etc | Festival - 1 week before
OPERATIONS | Ensure some seating is allocated at entrance's for elderly visitors | Festival - 1 week before
OPERATIONS | Oversee all big infrastructure assembly- must go up no later than Thursday prior to festival - Make sure GC Events assemble tents in the correct orientation with solid walls behind performance areas(necessary for media/TV etc) | Festival - 1 week before
OPERATIONS | Communicate with PROPERTY OWNERS regularly about the festival & site preparation activities - follow up regular mowing leading up to the Festival | Ongoing
OPERATIONS | Prepare car parking area/s - clear of rocks, sticks, holes, etc. | Ongoing
OPERATIONS | Regular communication with infrastructure providers to develop a good working relationship and keep abreast of new requirements as required | Ongoing
OPERATIONS | Develop and maintain an inventory of Stall needs and Infrastructure providers eg suppliers of tents/tables/chairs/cash drawers etc | Ongoing
PRODUCE | One week prior to the festival touch base with producers and arrange suitable collection time | Festival - 1 week before
PRODUCE | Maintain a database of producers contacts and the produce supplied | Ongoing
STALLHOLDERS | Peg out and spray site spaces | Festival - 1 week before
STALLHOLDERS | Print and laminate site plan + detailed list of stalls and site number | Festival - 1 week before
STALLHOLDERS | Attend festivals throughout year looking for new/potential stallholders. Network with existing stall holders | Ongoing
STALLHOLDERS | Check the list of goods intended to be sold by the stall holder listed on their application form– refuse some product if they don’t fit in with values of "YOUR EVENT" eg craft, product not made by stall holder or multi components eg coffee, biscuits, preserves etc. | Ongoing
STALLHOLDERS | Update database when applications are sent in. note power requirements and size of area needed | Ongoing
STALLHOLDERS | Respond to stall holder applications, questions, deny stalls if they don’t fit with "YOUR EVENT" values. | Ongoing
VOLUNTEERS | Send coordinators their final roster and contacts for their team, encouraging them to touch base (if they havent done so already) ensure all team members are ready for the event. | Festival - 1 week before
VOLUNTEERS | Maintain the volunteer roster; liaise with Coordinators to look at the gaps and consider how to fill them. Regularly recruit new volunteers. | Ongoing
Run Sheet Required

## Event D Day
AREA RESPONSIBLE | KEY TASK & MILESTONES | TIMELINE | ✔ | IS A RUN SHEET REQUIRED?
Bar | Be onsite to ensure Bar Marquee, ice trough and tables are set up on level ground | Festival Friday_Saturday
Bar | Be on site for the delivery of beer and wine and do a stock take to ensure it is all there | Festival Friday_Saturday
Bar | AT DAY END do a stock take - make notes of this for post festival report - collate how many/what is left over and determine what sold best, what didn't sell well and provide recommendations for the next event | "YOUR EVENT" Day
Bar | Set up the stall and decorate, ensuring that RSA and licensing signage is displayed according to guidelines | "YOUR EVENT" Day
BBQ | At day end - Do a stock take of what meat is left over and store it in the cold room - make notes of this for post festival report - the "YOUR EVENT" Exec will have advised you on what happens with any left overs - coordinate that - some will be used for the volunteer BBQ after "YOUR EVENT" | "YOUR EVENT" Day
BBQ | Coordinator is responsible for ensuring that all volunteers are adhering to the food safety guidelines | "YOUR EVENT" Day
BBQ | Ensure Food Handling guidelines are on display in the stall, and that adequate soap and hand towel is available for hand washing | "YOUR EVENT" Day
BBQ | Manage the stall and volunteers - the coordinator should not commit to a role on the day (e.g. cooking the BBQ) | "YOUR EVENT" Day
BBQ | Ensure that no food is to be consumed by volunteers near the BBQ area - ensure they go to the office/staff area for meals | "YOUR EVENT" Day
CHILDREN | Set up the kids activities | Festival Weekend
CHILDREN | Coordinate volunteers, answer questions and assist children | "YOUR EVENT" Day
"YOUR EVENT" EXEC | Coordinatre and oversee smooth flow of opening ceremony on the Friday before festival | Festival Friday_Saturday |  | Yes - Refer Opening Night Run Sheet
"YOUR EVENT" EXEC | Monitor flow of visitors through site, queues etc to make changes for next year | Festival Weekend
"YOUR EVENT" EXEC | Surveys | "YOUR EVENT" Day
FINANCE | Introduce the finance team to all the "YOUR EVENT" stall coordinators at the start of the day | "YOUR EVENT" Day
FINANCE | Work with Stallholder Coordinator to invoice & receive stallholder payments –send receipts to stall holder coordinator and follow up on late payments | Ongoing
MAIN MARQUEE | Ingredients - Source any last minute ingredients and perishables - Place any perishables in cold room - Prep any ingredients that need it the night before - Double check all pantry items are available | Festival Friday_Saturday
MAIN MARQUEE | Equipment - Double check equipment is all available - Obtain any last minute equipment | Festival Friday_Saturday
MAIN MARQUEE | Preparation and Wash Up area - Set up furniture and any large equipment - Make sure cold room is working - Make sure water and hot water is accessible - Put out bins/ and scrap bins - Organise/source any final/last minute equipment | Festival Friday_Saturday
MAIN MARQUEE | - Decorate marquee with sponsorship signs (not in view of future marketing opportunities, ie near stage for photos) | Festival Friday_Saturday
MAIN MARQUEE | - Organise Hot water access (urn hot water system etc) | Festival Friday_Saturday
MAIN MARQUEE | - Set up and decorate marquee | Festival Friday_Saturday
MAIN MARQUEE | MAIN MARQUEE SET UP - Decorate - Put up signage - Make sure sound and visual equipment is organized - Make sure cooking station is working - Make sure gas and electricity is working - Clean up Marquee through the day - Give sound and visual techs the program and run down of events | Festival Friday_Saturday
MAIN MARQUEE | - Set up Preparation Area | Festival Friday_Saturday
MAIN MARQUEE | INGREDIENTS - Source last minute ingredients from stall holders as they arrive - Store ingredients where appropriate - Prep ingredients as required - Clean up and return any ingredients as required | "YOUR EVENT" Day
MAIN MARQUEE | MAIN MARQUEE SET UP - Put out final decorations/perishables (ie Flowers/herbs) - Make sure sound and visual equipment is working and organized - day before and again festival morning - Put up final signage and program is displayed - Put out any recipe handouts - Remove rubbish as required | "YOUR EVENT" Day
MAIN MARQUEE | Marketing - Make sure signage is visible and appropriate - Make sure food labels are easy to be found - Place food labels on food as prepped so that chefs can endorse food as demonstrated. - Make sure handouts are given out - Make sure job lists are visible in prep area | "YOUR EVENT" Day
MAIN MARQUEE | Preparation and Wash Up area - Set up area with prep equipment which can be easily found (in see through crates or on shelving) - Tidy and clean as required - Help chefs Prep food and place on trays ready for demonstration - Clean up after prep and after presentations - Make sure prep area tidy and equipment and space is available for the next chef to prepare - Keep wash up area tidy and equipment cleaned asap - Remove rubbish as required | "YOUR EVENT" Day
MAIN MARQUEE | Volunteers - Welcome volunteers - Delegate tasks as required - Provide volunteers with job lists and requirements - Provide volunteers with refreshments - Thank volunteers and ask for feed back | "YOUR EVENT" Day
MAIN MARQUEE | - Provide chefs with "YOUR EVENT" aprons | "YOUR EVENT" Day
MAIN MARQUEE | Celebrity Chefs/Speakers + MC - Welcome chefs + MC and orientate them to Marquee and equipment - Give chefs a run down of program and expectations - Ask if there is anything else they may need - Introduce sound and TV tech to speakers and arrange mics etc | "YOUR EVENT" Day
MARKETING | Load surveys to the website | Festival Weekend
MC | Pre check with sound people well before the 9am start on Sunday | Festival Friday_Saturday
MC | Sound gear all set up on Saturday | Festival Friday_Saturday
MC | Communicate regularly with "YOUR EVENT" stalls re stock ("YOUR EVENT" stalls, P&Cs) and make relevant announcements throughout the day | "YOUR EVENT" Day
MC | Achieve balance between getting the announcements out and avoiding burdening the attendees with noise | "YOUR EVENT" Day
MC | Do all the outside announcements from 9am to 4pm close | "YOUR EVENT" Day
MC | Ensure celebs are at the correct locations at the correct times for outside events | "YOUR EVENT" Day
MC | Keep celebs and presenters informed and in the location where they need to be… | "YOUR EVENT" Day
MERCHANDISE | Deliver selected merchandise at other strategic places around festival site - e.g. bar for stubby holders, insulated bags with stalls selling product to keep cold - as pre arranged with relevant coordinators previously | Festival Friday_Saturday
MERCHANDISE | At day end - Stock take at end of the day - make notes for post festival report | "YOUR EVENT" Day
MUSIC | Set up signage and any decorations | Festival Friday_Saturday
MUSIC | Direct performers to the stage and ensure they have water and everything they need | "YOUR EVENT" Day
MUSIC | MC the music tent, ensuring a good flow of music throughout the day | "YOUR EVENT" Day
OPERATIONS | Erect ‘Entry’ sign for southern entrance with landscaping either side | Festival Friday_Saturday
OPERATIONS | Ensure that Sound & Visual have charged the mobile speaker up for festival day | Festival Friday_Saturday
OPERATIONS | Place donation barrels at each entrance with sign attached: Your Gold Coin Donation – Thank You | Festival Friday_Saturday
OPERATIONS | Ensure Stallholder Coordinator has enough Walkie Talkies for all direct stallholder volunteers | Festival Friday_Saturday
OPERATIONS | Coordinate the set up and pull down of fencing and signage once the traffic management role has been completed. | Festival Weekend
OPERATIONS | Coordinate the bump in of all infrastrsucture on site | Festival Weekend
OPERATIONS | Collect the lunch for the SES at the time agreed with BBQ coordinator | "YOUR EVENT" Day
OPERATIONS | Coordinate any communication between SES and MC during the day. Hold a debrief meeting with SES staff and "YOUR EVENT" volunteers once it is clear that the traffic management role has been completed on the day. | "YOUR EVENT" Day
OPERATIONS | Communicate with PROPERTY OWNERS regularly about the festival & site preparation activities - follow up regular mowing leading up to the Festival | Ongoing
OPERATIONS | Regular communication with infrastructure providers to develop a good working relationship and keep abreast of new requirements as required | Ongoing
PRODUCE | 1 – 2 days prior to the festival call producers and re confirm, store in cool room overnight | Festival Friday_Saturday
PRODUCE | Set up and decorate the "YOUR EVENT" site | Festival Friday_Saturday
PRODUCE | Maintain a database of producers contacts and the produce supplied | Ongoing
RAFFLES | Set up Raffles Marquee | Festival Friday_Saturday
RAFFLES | Use a number of volunteers to help with start of day if collecting prizes from stall holders. | "YOUR EVENT" Day
RAFFLES | Coordinate all sale points | "YOUR EVENT" Day
RAFFLES | Ensure the winners receive their prizes | "YOUR EVENT" Day
SIGNAGE | Erect all site signage | Festival Friday_Saturday
SIGNAGE | Monitor signage to ensure it has not been removed or wind damaged | "YOUR EVENT" Day
STALLHOLDERS | Mark out site with site numbers – Liaise with helpers – orientation of site plan/stalls – ensure they have copies of site plan and stall holder list | Festival Friday_Saturday
STALLHOLDERS | Liaise with electrician – ensure all power requirements are safe and working | Festival Weekend
STALLHOLDERS | Ensure stall holders are settled, setup and vehicles are off site by 8am | "YOUR EVENT" Day
STALLHOLDERS | Mark off stall holders as they arrive | "YOUR EVENT" Day
STALLHOLDERS | Set up and monitor the smooth flow of presenters into the Appeciation Tent - ensure it is kept clean and tidy between presentations and ensure speakers are briefed 15minutes before their talk | "YOUR EVENT" Day
STALLHOLDERS | Monitor stalls during the day – check they are happy and are selling what was agreed to. Get feedback from stalls during the day. Note general feel from the stallholders | "YOUR EVENT" Day
STALLHOLDERS | Attend festivals throughout year looking for new/potential stallholders. Network with existing stall holders | Ongoing
STALLHOLDERS | Check the list of goods intended to be sold by the stall holder listed on their application form– refuse some product if they don’t fit in with values of "YOUR EVENT" eg craft, product not made by stall holder or multi components eg coffee, biscuits, preserves etc. | Ongoing
STALLHOLDERS | Update database when applications are sent in. note power requirements and size of area needed | Ongoing
STALLHOLDERS | Respond to stall holder applications, questions, deny stalls if they don’t fit with "YOUR EVENT" values. | Ongoing
VOLUNTEERS | Reallocate volunteers to areas if necessary - ensuring everyone has adequate support | Festival Weekend
VOLUNTEERS | Hand over name tags/lanyards for volunteers and farmers as they arrive | Festival Weekend
VOLUNTEERS | Coordinate floaters and roamers and be a support person during the day…. | "YOUR EVENT" Day
VOLUNTEERS | Ensure stalls/coordinators have enough helpers | "YOUR EVENT" Day
VOLUNTEERS | Coordinate Volunteer roster at informaion tent | "YOUR EVENT" Day
VOLUNTEERS | Maintain the volunteer roster; liaise with Coordinators to look at the gaps and consider how to fill them. Regularly recruit new volunteers. | Ongoing

## EXAMPLE_OPENING NIGHT RUN SHEET
Opening Night - DATE - TIME - LOCATION
| Contact | Email | Phone | What are they providing? | Cost | Paid | Ordered | Still to do:
Music |  |  |  | Shane | 0 | 0 | Jen | Left two messages with Shane 16/3/2016 - Talk to Shane RE: if can do acoustic - cancel Hayley
Food |  |  |  | ANTIPASTO x 2 Marinated artichokes Roast capsicum Grilled eggplant Semi dried tomatoes Olives Sourdough cracker Feta CHEESE PLATTER x 1 CURED MEAT PLATTER x 1 Selection of cured meats and asparagus. Glazing of ham $50. | 370 | Need to receive invoice from Joy - follow her up for this. | Yes done | Jen to pick up Ham from Deb/Ashtons on Tuesday 5 April - drop in ham to Joy/Wendlend on Wednesday 6 April. Pickup all food 3.30pm Friday 8 April
Fridge |  |  |  | Yes Fridge should be right to go. Ian was ordering it today (16 March) and apparently they are in Brisbane so shouldn't take to long to get it up |  |  |  | Follow up with Ian
Carving / serving of Ham |  |  |  | Carving of ham on sponsor night - Dave H? Breads to be Pita Bread (or similar) cut into quarters. Condiments include mustard, friendship food beetroot sauce, hummus, tomato relish | 40 |  | Jen / Dave H | Jen will provide ham board, Dave H knife, platters and condiments. Purchase Pita Bread & extra condiemnts Friday 8 April
Glassware |  |  |  | 4 doz red wine glasses; 2 doz champagne glasses; 4 doz water goblets | 79.85 |  | Yes done | Will deliver to festival site Wed with marquees - Vicki Whan has arranged to deliver glassware to the hall
Beer |  |  |  | 70 cartons ordered for festival |  |  | Linda | Have 2.5 cartons already - Deb can pick up beer after Easter
Beer Serving Bucket |  |  |  | Beer bucket for serving of beer & bottle opener |  |  | Yes - Deb | Deb has three buckets for beer
Wine |  |  |  | 6 cartons verdelho; 3 cartons Rose & 3 cartons Cab Sav ordered for use at sponsors night & festival |  |  | DEB | The rest can be used at the festival
Champagne |  |  |  | 3 cartons | 0 |  | DEB | In Fridge
Water |  |  |  | 3 x water jugs - glasses provided |  |  | Jen / Deb | Stainless steel water jug - Jen has one, Deb has two
Mineral Water |  |  |  | Purchase 10 larger bottles of sparkling to go in beer bucket? | 7.5 |  | Deb H | Deb will purchase 10
Non Alcoholic Punch |  |  |  | Jen to purchase ingredients and make this up in dispenser - ginger beer, juice, lemonade & fruit | 50 |  | Jen | Purchase supplies from Coles Wed 8 April
Pouring drinks |  |  |  | Hugh to pour on the night? |  |  |  | Ask Hugh to be in charge of top ups
Ice |  |  |  | 5 bags ice | 22.5 |  | Jen to Pick Up Friday | Jen to pickup on Friday
Esky |  |  |  | Provide Esky for Beer | 0 |  |  | Dave to bring / will have fridge
Tables |  |  |  | Utilise 3 x tables 2.41 x .91 in dimension. 3 x tableclothes ordered GC Events | 30 |  | Yes done | Tablecloths ordered
Table Décor |  |  |  | 2 x large bushy arrangements of natural leaf. Flowers for table - To be in two tall buckets to break up the table & give it height - in similar theme to lunch arrangement- | 200 |  | Yes done | Jen to pick up on Friday - arrangements to be used in Main Marquee for Festival Day - Jen to return the buckets to Bec afterwards
Napkins |  |  |  | Deb has orderd 2 ply for the bar - will use some of these | 0 |  | Deb H | Follow up with Deb
Speakers |  |  |  | Linda is MC - speakers are TEQ; USQ; Artists (Virgina Hanlon); Deb House |  |  | Linda | Running Sheet for Linda; email all speakers?
Toilets | [7 empty] | Jen Follow up with Ian - Portaloos are avail on standby
Artists |  |  |  | Sorted |  |  | Lisa | xx
Working Bee |  |  |  | Clean hall prior to the event? Monday 4 April please |  |  |  | Jen to follow up with Ian Easter
799.85